## Worksheet
KPI Monitoring - Order Tracker (Planning View)
Order ID | Customer Name | Product/Service | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | KPI Target (Days) | KPI Achieved (Days) | KPI Status
ORD-2024-001 | Global Tech Solutions | Software Integration Package | 2024-01-15 | 2024-03-31 | 2024-01-15 | 2024-03-30 | Completed | 75 | 75 | Met Target
ORD-2024-002 | InnovateCorp Inc. | Data Migration Service | 2024-01-18 | 2024-05-15 | 2024-01-18 | Not Started | In Progress | 120 | N/A | On Track
ORD-2024-003 | Future Systems Ltd. | Cloud Infrastructure Setup | 2024-02-10 | 2024-06-30 | 2024-03-15 | N/A | Delayed | 140 | N/A | At Risk
ORD-2024-004 | NextGen Enterprises | UI/UX Design Project | 2024-01-25 | 2024-03-15 | 2024-01-30 | 2024-03-16 | Delayed | 50 | 51 | Missed Target
ORD-2024-005 | EcoEnergy Group | Renewable Energy Report | 2024-03-15 | 2024-05-31 | N/A | N/A | Pending Start | 78 | N/A | On Track (Planned)
ORD-2024-006 | SmartCity Inc. | IoT Integration System | 2024-04-15 | 2025-01-31 | N/A | N/A | Pending Start | 260 | N/A | On Track (Planned)
Total Orders: | [9 empty] | 6
Note:This table represents a planning view for KPI monitoring of orders. Status indicators are based on planned vs actual timelines.