## KPI Monitoring - Project Plan
Project ID | Project Name | Start Date | End Date | Status | KPI Target | KPI Actual | Variance (Target - Actual)
P001 | Website Redesign Launch | 2024-01-15 | 2024-03-31 | In Progress | 95% | 87% | -8%
P002 | Campaign X - Q1 Marketing | 2024-01-10 | 2024-03-31 | On Track | 5,000 Leads | 4,856 Leads | -144 Leads
P003 | Product Integration Phase 1 | 2024-02-01 | 2024-06-30 | Delayed | 98% Uptime | 91% Uptime | -7%
P004 | User Onboarding Improvement | 2024-03-01 | 2024-12-31 | On Track | 85% Completion Rate | 86% Completion Rate | +1%
Total Projects: |  |  |  |  | 4 | 4 | -1%
This KPI Monitoring Template is for internal business use. Data updated as of May 30, 2024.