## KPI Monitoring - Client View
KPI Monitoring - Project Plan (Client View)
Project Phase | Key Objective | KPI | Target Value | Current Value | Status | Scheduled Completion Date
Planning & Initiation | Define project scope and stakeholders | Scope Document Approved (%) | 100% | 95% | In Progress | 2024-10-15
Design & Development | Create core system architecture and features | Feature Implementation Rate (%) | 85% | 72% | In Progress | 2024-11-30
Testing & QA | Ensure system reliability and performance | Bug Resolution Rate (%) | 95% | 87% | In Progress | 2024-12-15
Deployment | Roll out system to production environment | Deployment Success Rate (%) | 98% | 0% | Delayed | 2025-01-10
Post-Launch Support | Monitor performance and support users | User Satisfaction Score (CSAT) | 4.7/5.0 | 4.3/5.0 | In Progress | 2025-03-31
Client View - Last Updated: October 5, 2024 ¦ Version v1.3