## Worksheet
DAILY PROJECT PLAN - KPI MONITORING
Date | Project Phase | Task Name | Assigned To | Expected Start Time | Expected End Time | Status | KPI Target (Value) | KPI Actual (Value) | KPI Progress (%) | Risk Level | Notes
2024-04-05 | Planning | Project Kick-off Meeting | Jane Smith | 09:00 AM | 11:30 AM | Completed | 1 | 1 | 100% | Low | Made all necessary introductions.
2024-04-05 | Design | Create Wireframes | Mike Johnson | 13:00 PM | 16:30 PM | In Progress | 2.5 hrs / task | 1.8 hrs / task | 72% | Medium | On track, minor delay due to feedback loop.
2024-04-05 | Development | Backend API Setup | Alex Brown | 10:00 AM | 13:30 PM | Pending Start | 2.5 hrs / task | - (Not Started) | 0% | Low | Waiting on server access.
Daily Summary
Total Tasks: |  |  | 3 |  |  |  | Completed: | 1 (33%) | In Progress: | 1 (33%)
Overall KPI Progress (Weighted Average) | [5 empty] | 58%