## Worksheet
KPI Monitoring - Detailed Project Plan
Task ID | Task Description | Owner | Start Date | End Date | Status | KPI Target | KPI Actual (Progress) | % Complete
TP001 | Project Initiation & Planning | Jane Smith | 2024-04-01 | 2024-04-15 | On Track | KPI 1: Documented Project Scope (1) | Completed & Approved | 100%
TP002 | Resource Allocation & Team Onboarding | Mark Johnson | 2024-04-16 | 2024-04-30 | On Track | KPI 2: Team Mobilization (15 team members) | 15 assigned, onboarding completed (April 30) | 100%
TP003 | Requirements Gathering & Validation | Sarah Lee | 2024-05-01 | 2024-05-15 | On Track | KPI 3: 100% Requirements Signed Off (by stakeholders) | 98% validated, pending final sign-off | 98%
TP004 | Design Phase (UI/UX & System Architecture) | Alex Chen | 2024-05-16 | 2024-06-15 | On Track | KPI 4: All Design Documents Approved (3) | Designs completed for 3 modules; awaiting review | 80%
TP005 | Development Sprint 1 (Core Features) | Tina Brown | 2024-06-16 | 2024-07-31 | On Track | KPI 5: 85% Code Coverage (Unit Tests) | 78% achieved after Sprint 1 | 76%
TP006 | Quality Assurance & Testing (UAT) | Daniel Kim | 2024-08-01 | 2024-09-30 | Delayed | KPI 6: 15+ Test Cases Executed (UAT) | Only 8 test cases executed (due to dependency issues) | 53%
TP007 | Deployment & Go-Live Preparation | Lisa White | 2024-10-01 | 2024-10-31 | Completed | KPI 7: Successful Production Deployment (Zero Critical Bugs) | Deployment completed successfully; zero critical issues reported | 100%
Overall Project Progress: | [6 empty] | 84%
Note:This table is a live KPI monitoring template for project tracking. Status indicators are updated weekly. KPIs are measured against baseline targets set at project kickoff.