## Worksheet
KPI Monitoring - Project Plan - Financial View
Project Phase | KPI Indicator | Financial Metrics (USD) |  |  | Performance Tracking
|  | Target Budget | Actual Spend | Variance (USD) | Status | Progress % | Forecasted Completion Date
Initiation Phase | Project Charter Approval | $50,000 | $48,500 | $1,500 (Favorable) | On Track | 10% | Jan 31, 2025
| Budget Validation & Approval | $75,000 | $73,800 | $1,200 (Favorable) | On Track | 15% | Feb 15, 2025
Planning Phase | Resource Allocation Plan | $120,000 | $125,400 | ($5,400) (Unfavorable) | At Risk | 35% | Mar 20, 2025
| Risk Assessment & Mitigation Plan | $45,000 | $43,200 | $1,800 (Favorable) | On Track | 45% | Apr 10, 2025
| Project Schedule Development | $60,000 | $62,100 | ($2,100) (Unfavorable) | At Risk | 55% | Apr 25, 2025
Execution Phase | Development & Build | $450,000 | $438,900 | $11,100 (Favorable) | On Track | 72% | Jun 30, 2025
| Testing & QA Phase | $180,000 | $192,300 | ($12,300) (Unfavorable) | At Risk | 68% | Jul 15, 2025
| User Training & Onboarding | $90,000 | $87,600 | $2,400 (Favorable) | On Track | 75% | Aug 10, 2025
Closure Phase | Final Reporting & Handover | $40,000 | $38,500 | $1,500 (Favorable) | On Track | 95% | Sep 30, 2025
| Post-Implementation Review | $30,000 | $31,800 | ($1,800) (Unfavorable) | At Risk | 92% | Oct 15, 2025
Total (All Phases) | Total Budget vs Actual | $1,090,000 | $1,135,400 | ($45,400) (Unfavorable) | Overall Project Health: At Risk
Reporting Period:Q1 2025 ¦Last Updated:April 5, 2025
This financial view of the project plan reflects key KPIs aligned with budget and performance tracking.