## KPI Monitoring - Project Plan
KPI Monitoring - Project Plan (Large Business Style)
Project ID | Project Name | Owner | Start Date | Target End Date | Status | KPI 1: Completion % (Target) | KPI 2: Budget Utilization (%) (Target) | KPI 3: Risk Level
PROJ-001 | Enterprise Cloud Migration | Sarah Thompson | 2024-07-01 | 2024-11-30 | In Progress | 65% (85%) | 58% (75%) | Medium Risk
PROJ-002 | CX Enhancement Initiative | James Wilson | 2024-06-15 | 2024-10-15 | Completed | 100% (100%) | 89% (95%) | Low Risk
PROJ-003 | Data Analytics Platform Upgrade | Lisa Chen | 2024-07-10 | 2024-12-31 | In Progress | 45% (65%) | 38% (50%) | High Risk
PROJ-004 | Sustainability Program Rollout | Michael Rodriguez | 2024-08-01 | 2025-03-31 | In Progress | 35% (50%) | 28% (40%) | Low Risk
PROJ-005 | Cybersecurity Framework Modernization | Alice Johnson | 2024-06-25 | 2024-11-30 | Delayed (Revised: 2025-01-31) | 78% (90%) | 67% (85%) | High Risk
Last Updated:October 26, 2024 ¦ Prepared by: Executive Planning Office