## Worksheet
KPI Monitoring - Project Plan (Manager View)
Project Phase | Key Task | Responsible | Start Date | Target Date | Status | KPI Metric | Target Value | Current Value | Variance (±)
Initiation | Define Project Scope & Objectives | John Smith | 2023-10-05 | 2023-10-15 | Complete | Budget Adherence | $50,000 | $48,750 | +1.2%
| Secure Stakeholder Approval | Jane Doe | 2023-10-16 | 2023-10-31 | Complete | Approval Rate | 95% | 97% | +2.0%
Planning | Create Detailed Work Breakdown Structure (WBS) | Robert Lee | 2023-11-01 | 2023-11-15 | Complete | WBS Accuracy Rate | 98% | 99% | +1.0%
| Develop Project Schedule & Timeline | Sarah Kim | 2023-11-16 | 2023-12-05 | In Progress | Timeline Adherence (%) | 95% | 87% | -8.0%
| Risk Assessment & Mitigation Plan | Marcus Brown | 2023-12-06 | 2023-12-15 | Delayed | Risk Coverage Score | 90% | 78% | -12.0%
Execution | Team Onboarding & Training | Lisa Chen | 2024-01-01 | 2024-01-15 | In Progress | Training Completion Rate | 95% | 86% | -9.0%
| Development & Implementation Phase | Daniel Torres | 2024-01-16 | 2024-03-31 | On Hold (Pending Approval) | Code Quality Score (SonarQube) | ≥ 85% | 79% | -6.0%
| Daily Status Reporting & Monitoring | Amy Wong | 2024-01-01 | 2024-06-30 | Complete (Ongoing) | Reporting Accuracy (%) | 98% | 97% | -1.0%
Project Summary & Overall KPIs
Overall Schedule Performance Index (SPI): |  |  |  | 0.92 (On Track – Slight Delay)
Overall Cost Performance Index (CPI): |  |  |  | 0.97 (On Budget – Minor Overspend)
Overall Project Health Score: |  |  |  | 83% (Moderate Risk)
* Data refreshed on October 10, 2023 ¦ Manager View – Real-Time KPI Monitoring