## KPI Monitoring - Project Plan
KPI Monitoring - Project Plan (Multi Page)
Project Name | Start Date | End Date | Status | KPI Target | KPI Current Value
Website Redesign Initiative | 2024-01-15 | 2024-06-30 | In Progress | 95% | 87%
Mobility App Launch | 2024-03-10 | 2024-11-30 | In Progress | 98% | 89%
CX Optimization Program | 2024-05-25 | 2025-01-15 | Pending Start | 93% | N/A
KPI Name | Target Value | Current Value | Status (Green/Yellow/Red) | Last Updated
User Engagement Rate | 95% | 87% | Yellow | 2024-06-10
Avg. Load Time (ms) | < 1500 | 1634 | Red | 2024-06-15
CX Satisfaction Score (CSAT) | 93% | 89% | Yellow
Milestone | Due Date | Actual Completion Date
Project Kick-off Meeting | 2024-01-15 | 2024-01-15
User Research Completion | 2024-03-31 | 2024-03-31
Design Approval (Phase 1) | 2024-05-15 | Not Started
Beta Release Test Phase | 2024-10-31 | N/A
Website Redesign Initiative | (87%)
Mobility App Launch | (64%)
CX Optimization Program | (21%)
Task/Activity | Responsible Team
UI/UX Design | Product & Design Team
Frontend Development | Engineering - Web Team
Data Integration (APIs) | Backend Engineering Team
User Testing & Feedback Loop | CX & QA Team
Risk | Probability (Low/Med/High)
Delays in third-party API integration | High
User adoption lower than expected post-launch | Medium
Budget overrun due to scope creep | Medium
Template Version:Multi-Page Project Plan (KPI Monitoring)
Last Updated:June 20, 2024
This document is intended for internal KPI tracking and project monitoring. All data is sourced from real-time dashboards and weekly reviews.
For updates or adjustments, contact: kpi-monitoring@company.com