## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Status | KPI Target | KPI Actual (Current) | KPI Variance (%)
T001 | Project Kickoff | John Doe | 2024-01-15 | 2024-01-17 | In Progress | Completed by 17/01/2024 | Completed on 16/01/2024 | -5.88%
T002 | Requirements Gathering | Jane Smith | 2024-01-18 | 2024-01-31 | Delayed | 95% completeness by 31/01/2024 | 87% completeness (as of 30/01/2024) | -8.42%
T003 | Design Phase | Mike Johnson | 2024-02-01 | 2024-02-15 | Scheduled | Final designs approved by 15/02/2024 | N/A (Not started) | -100.0%
T004 | Development Sprint 1 | Sarah Lee | 2024-02-16 | 2024-03-01 | Scheduled | 85% functionality delivered by 01/03/2024 | N/A (Not started) | -100.0%
T005 | Testing Phase | David Brown | 2024-03-18 | 2024-04-15 | Scheduled | All critical bugs resolved by 15/04/2024 | N/A (Not started) | -100.0%
Overall KPI Performance: | [6 empty] | 82.3% | +4.6%