## Worksheet
KPI Monitoring - Project Plan Summary View
Project Name | Phase/Task | Start Date | End Date | Budget (USD) | Status | KPI Target | KPI Actual / Progress (%)
Product Launch 2024 | Market Research | 01-Jan-2024 | 15-Feb-2024 | $75,000 | Completed | Survey 1,500 customers | 1,632 / 108.8%
Product Launch 2024 | Design & Prototyping | 16-Feb-2024 | 31-Mar-2024 | $150,000 | On Hold | Finalize 3 prototype versions | 1.8 / 60%
Product Launch 2024 | Development & Testing | 01-Apr-2024 | 31-May-2024 | $350,000 | Delayed | Complete 95% test coverage | 78 / 82%
Product Launch 2024 | User Acceptance Testing (UAT) | 01-Jun-2024 | 30-Jun-2024 | $50,000 | Not Started | Test with 50 internal users | — / 0%
Project Summary |  |  |  | $625,000 | Overall Status: On Hold (3/4 Tasks) | Target Completion: 92% | 75% Average Progress
Last updated: 05-Apr-2024 ¦ Data source: Project Management System v3.1