## Worksheet
KPI Monitoring - Project Plan Tracking View
Task ID | Task Description | Owner | Start Date | End Date | Baseline Duration (Days) | Status | KPI Target (%) | KPI Actual (%) | Progress Status
TASK-001 | Project Initiation & Planning | Alice Johnson | 2024-04-01 | 2024-04-15 | 15 | At Risk | 95% | 87% | Delayed
TASK-002 | Requirements Gathering | Bob Smith | 2024-04-16 | 2024-05-15 | 30 | At Risk | 98% | 93% | Delayed
TASK-003 | Design Phase Completion | Carol Davis | 2024-05-16 | 2024-06-30 | 45
TASK-004 | Development Sprint 1 | Dave Wilson | 2024-07-01 | 2024-07-31 | 31 | At Risk | 96% | 89% | Delayed
TASK-005 | Testing & QA Validation | Eva Brown | 2024-08-01 | 2024-08-31 | 31 | At Risk | 95% | 94% | Delayed
TASK-006 | Deployment & Go-Live | Frank Lee | 2024-09-01 | 2024-09-15 | 15 | Delayed | 98% | 96% | Delayed
Total Tasks: | [7 empty] | 6 | Achieved (3)
Last Updated:April 5, 2024 ¦Reporting Period:Q2 2024