## KPI Monitoring - Financial View
KPI Monitoring - Financial View (Project Template)
Project ID | Project Name | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Budget Variance (USD) | % of Budget Spent | Forecasted Cost (USD) | Revenue Generated (USD) | Net Profit (USD) | Status
PJ001 | Infrastructure Upgrade | 2024-01-15 | 2024-06-30 | $5,500,000.00 | $4,897,356.89 | $602,643.11 (Favorable) | 89% | $5,250,000.00 | $7,234,567.89 | $2,337,211.01 | On Track
PJ002 | Software Development Phase II | 2024-03-10 | 2024-11-30 | $8,750,000.00 | $6,987,564.32 | $1,762,435.68 (Favorable) | 80% | $9,100,000.00 | $12,543,219.76 | $5,555,655.44 | At Risk
PJ003 | Marketing Campaign Q2 | 2024-04-01 | 2024-06-30 | $1,550,897.65 | $1,789,345.23 | -$238,447.58 (Unfavorable) | 115% | $1,600,000.00 | $3,219,876.45 | $1,430,531.22 | Over Budget
PJ004 | Research & Development Lab Setup | 2024-01-25 | 2025-12-31 | $6,890,347.89 | $4,356,789.11 | $2,533,558.78 (Favorable) | 63% | $7,000,000.00 | $4,987,654.32 | $-125,345.68 | At Risk
PJ005 | Global Expansion Initiative | 2024-05-15 | 2026-12-31 | $18,999,765.43 | $7,876,432.90 | $11,123,332.53 (Favorable) | 41% | $20,500,000.00 | $9,876,543.89 | $-123,456.11 | On Track
Totals |  |  |  | $41,691,008.99 | $25,807,535.45 | $15,883,473.54 (Favorable) | 62% | $42,900,000.00 | $37,861,852.21 | $9,164,594.98