## Worksheet
Project Phase | Key Milestones |  |  |  | KPIs & Targets |  |  | Status
| Task Name | Planned Start | Planned End | Actual End | KPI Metric | Target Value | Actual Value
Initiation Phase | Project Charter Approval | 2023-09-01 | 2023-09-15 | 2023-09-14 | Budget Utilization Rate | ≤ 5% | 4.8% | On Track
Planning Phase | Resource Allocation Plan Finalized | 2023-09-16 | 2023-10-05 | 2023-10-04 | Risk Mitigation Coverage (%) | ≥ 95% | 96.7% | Completed
Execution Phase | Demo Version Delivery | 2023-10-06 | 2023-11-30 | 2023-11-28 | User Satisfaction Score (NPS) | ≥ 75 | 78.4 | Completed
Monitoring & Control | Milestone Review Meeting (Q4) | 2023-11-01 | 2023-11-30 | 2023-11-30 | Bug Resolution Rate (%) | ≥ 98% | 98.6% | Completed
Closure Phase | Final Project Review & Sign-Off | 2023-12-01 | 2024-01-15 | - | On-Time Delivery Rate (%) | ≥ 95% | 93.2% | Delayed
Overall Project Performance: | [5 empty] | 93.5% | 93.5% | Delayed