## Worksheet
Project Phase | Q1 (Jan - Mar) |  |  |  | Q2 (Apr - Jun) |  |  |  | Q3 (Jul - Sep) |  |  | Q4 (Oct - Dec)
| Target | Actual | KPI | Status | Target | Actual | KPI
Initiation & Planning | 50% | 48% |  | Delayed | 75% | 72% |  | Delayed | 85% | 87% | On Track | 95% | 97% | On Track
Design & Development | 60% | 63% |  | On Track | 70% | 68% |  | Delayed | 85% | 83% | Delayed | 95% | 94% | Delayed
Testing & QA | 45% | 42% |  | Delayed | 65% | 72% |  | On Track | 90% | 88% | Delayed | 100% | 102% | On Track
Deployment & Go-Live | 20% | 18% |  | Delayed | 45% | 47% |  | On Track | 70% | 73% | On Track | 100% | 103% | On Track
Total Performance (Avg) | 97% |  |  | On Track | 98% |  |  | On Track | 96% |  | Delayed | 102% |  | On Track
Annual KPI Monitoring Dashboard - Project Timeline ¦ End of Year Summary