## Worksheet
KPI Monitoring - Project Timeline (Client View)
Project Performance Tracking & Milestone Overview
Phase / Milestone | Start Date | Target End Date | Actual End Date | Status | KPI Target(Success Threshold) | KPI Actual Result(Current Value) | Progress (%)
Project Initiation & Planning | 2024-01-05 | 2024-01-28 | 2024-01-30 | Delayed | Completed by 1/28/24(95% completion) | 100%(On Time) | 100%
Requirement Gathering | 2024-01-31 | 2024-03-15 | 2024-03-18 | Delayed | Stakeholder sign-off by 3/15/24(98% feedback) | 96%(Minor revisions pending) | 96%
Design & Prototyping | 2024-03-19 | 2024-05-10 |  | Ongoing | Final mockups approved by 5/10/24(All UX checks passed) | 78%(In review) | 78%
Development Phase I | 2024-05-13 | 2024-07-19 |  | Ongoing | Core modules functional by 7/19/24(85% unit testing) | 62%(Testing in progress) | 62%
QA & Testing | 2024-07-22 | 2024-09-15 |  | Ongoing | All critical bugs resolved by 9/15/24(0 high-priority issues) | 30%(Defects found: 12) | 30%
User Acceptance Testing (UAT) | 2024-09-18 | 2024-10-31 |  | Ongoing | UAT sign-off by 10/31/24(95% user satisfaction) | 25%(Feedback collection in progress) | 25%
Go-Live & Deployment | 2024-11-01 | 2024-11-30 |  | Ongoing | Full production rollout complete by 11/30/24(99.9% uptime) | 5%(Pre-deployment checks) | 5%
Total Project Progress |  |  |  | Overall Status | Avg. KPI Achievement(Target vs Actual) | Overall KPI Score(Out of 100)