## Worksheet
KPI Monitoring Dashboard - Project Timeline
Project Phase | Start Date | End Date | Status | KPI Target | KPI Actual | Variance (Actual - Target)
Project Initiation | 2023-10-01 | 2023-10-15 | Completed | 3.5 MRR | 4.2 MRR | +0.7 MRR
Requirements Analysis | 2023-10-16 | 2023-11-05 | Completed | 8.7 KPIs Defined | 9.2 KPIs Defined | +0.5 KPIs
Design Phase | 2023-11-06 | 2023-11-30 | In Progress | 45% Design Completion | 68% Design Completion | +23%
Development Sprint 1 | 2023-12-01 | 2024-01-15 | In Progress | 3.8 Features Delivered | 4.7 Features Delivered | +0.9 Features
Testing & QA | 2024-01-16 | 2024-03-15 | Delayed (Est.) | 98% Test Coverage | 87% Test Coverage | -11%
User Training | 2024-03-16 | 2024-04-30 | Pending | 15 Users Trained | N/A | -
Go-Live & Launch | 2024-05-01 | 2024-05-31 | Pending | 1.8 MRR Post-Launch | N/A | -
Overall Project Health
Total Phases Completed:2/7¦ On Track Phases:3/7¦ Delayed Tasks:1
Overall KPI Trend:Positive (Average Variance +0.6 MRR / +9%)