## Worksheet
KPI Monitoring - Project Timeline (Detailed)
Project Phase | Task Description | Start Date | Target End Date | Actual End Date | Status | KPI Indicator (%) | Responsible Team/Person | Milestones Achieved (%)
Phase 1: Project Planning | Define project scope and objectives | 2024-01-05 | 2024-01-15 |  | In Progress | 95% | Jane Doe (PM) | 80%
| Create detailed project schedule & Gantt chart | 2024-01-16 | 2024-01-31 |  | In Progress | 90% | Mike Smith (Scheduler) | 65%
| Finalize budget allocation and resource planning | 2024-01-20 | 2024-01-31 |  | In Progress | 85% | Sarah Lee (Finance) | 75%
Phase 2: Design & Development | Develop system architecture and technical design | 2024-02-01 | 2024-03-15 |  | In Progress | 78% | Tom Brown (Lead Dev) | 60%
| Create UI/UX prototypes and user flows | 2024-02-15 | 2024-03-10 |  | In Progress | 88% | Lisa Wong (Design) | 70%
| Complete backend development and API integration | 2024-03-16 | 2024-05-15 |  | In Progress | 75% | Alex Chen (Backend) | 40%
| Implement front-end components and responsive design | 2024-03-16 | 2024-05-31 |  | In Progress | 70% | Rita Patel (Frontend) | 35%
Phase 3: Testing & QA | Develop test cases and scripts | 2024-06-01 | 2024-06-15 |  | In Progress | 95% | Dan Wilson (QA Lead) | 85%
| Execute functional, integration & regression testing | 2024-06-16 | 2024-07-31 |  | In Progress | 85% | Linda Garcia (QA) | 50%
Phase 4: Deployment & Go-Live | Prepare deployment package and staging environment | 2024-08-01 | 2024-08-15 |  | In Progress | 93% | Chris Taylor (Ops)
| Deploy to production and monitor post-launch performance | 2024-08-16 | 2024-09-30 |  | In Progress
Phase 5: Post-Implementation Review | Conduct project retrospective and lessons learned session | 2024-10-01 | 2024-10-15
| Finalize documentation and handover to operations team | 2024-10-16 | 2024-10-31
Note:This KPI Monitoring Template tracks project milestones, performance indicators, and responsible personnel. Status indicators are updated weekly.