## KPI Monitoring - Employee View
Employee Name | Project Name | KPI Objective | Start Date | Target Completion Date | Milestones / Tasks | Status (Progress)
Jane Doe | Website Redesign Initiative | Increase user engagement by 25% within Q3 | 2024-06-01 | 2024-08-31 | - UI/UX Mockups: Completed (June 15) - Frontend Development: In Progress (Due July 30) - QA Testing & Feedback: Scheduled (Aug 15) - Launch & Analytics Tracking: Planned (Aug 31) | 68%
John Smith | CRM System Integration | Implement CRM integration by July 31 to improve client follow-up time by 40% | 2024-05-15 | 2024-07-31 | - Requirements Gathering: Completed (May 31) - API Configuration: Completed (June 30) - Data Migration: In Progress (Due July 25) - Team Training & Go-Live: Scheduled (July 31) | 100%
Alice Brown | Customer Onboarding Automation | Reduce onboarding time from 5 days to under 24 hours by end of Q3 | 2024-07-01 | 2024-09-30 | - Process Analysis: Completed (July 15) - Workflow Design: In Progress (Due Aug 15) - Tool Development: Planned (Aug 20) - Pilot Testing & Rollout: Scheduled (Sep 30) | 42%
Robert Wilson | Internal Training Program Revamp | Launch 5 new training modules by September 15 to improve team skill development | 2024-06-10 | 2024-09-15 | - Content Outline Finalized: Completed (June 30) - Module 1 & 2 Development: In Progress (Due Aug 5) - Module 3 & 4 Recording: Scheduled (Aug 20) - Final Review & Launch: Planned (Sep 15) | 38%