## Worksheet
KPI Monitoring - Project Timeline (Extended Version)
Project Phase | KPI Indicator | Target Value | Actual Value | Status | Scheduled Start Date | Scheduled End Date | Actual Start Date | Actual End Date
Initiation Phase | Stakeholder Approval Rate | 100% | 95% | On Track | 2023-09-01 | 2023-09-15 | 2023-09-01 | 2023-09-14
| Budget Approval Rate | 100% | 98% | On Track | 2023-09-16 | 2023-10-15 | 2023-09-16 | 2023-10-14
| Project Charter Signed | Yes (1) | Yes (1) | Achieved | 2023-09-16 | 2023-10-15 | 2023-10-14 | 2023-10-14
Planning Phase | Project Plan Completeness (%) | 95% | 93% | On Track | 2023-10-16 | 2023-11-30 | 2023-10-16 | 2023-11-35
| Risk Assessment Completion Rate | 100% | 97% | On Track | 2023-10-16 | 2023-11-30 | 2023-10-17 | 2023-11-35
| Benchmarking Results Reviewed | Yes (1) | Yes (1) | Achieved | 2023-10-25 | 2023-11-30 | 2023-11-15 | 2023-11-35
| Resource Allocation Confirmed | 98% | 96% | Delayed | 2023-10-16 | 2023-11-30 | 2023-11-5 | Not Complete
Execution Phase | Task Completion Rate (Weekly) | ≥90% | 92% | On Track | 2023-12-01 | 2024-03-31 | 2023-12-01 | Not Complete
| Bug Fix Resolution Time (Avg) | <48 hrs | 56 hrs | Delayed | 2023-12-01 | 2024-03-31 | 2023-12-5 | Not Complete
| Quality Assurance Pass Rate | 98% | 97.5% | On Track | 2023-12-01 | 2024-03-31 | 2023-12-5 | Not Complete
| User Acceptance Testing (UAT) Completion | Yes (1) | In Progress | On Track | 2023-12-08 | 2024-03-31 | 2024-1-5 | Pending
Closing Phase | Final Deliverable Sign-off Rate | 100% | 90% | Delayed | 2024-04-01 | 2024-05-31 | Not Started | Pending
| Project Evaluation Score (Avg) | ≥8.5/10 | 8.2/10 | Delayed | 2024-04-01 | 2024-05-31 | Not Started | Pending
| Closed Project Documentation Rate | 100% | 85% | Delayed | 2024-04-15 | 2024-05-31 | Not Started | Pending
Overall Project Status: On Track (with minor delays) |  |  |  | Completion Progress:76%
Last updated: April 03, 2024 ¦ Prepared for KPI Monitoring Dashboard