## Worksheet
KPI Monitoring - Project Timeline (Freelancer Style)
Task ID | Task Description | Start Date | End Date | Status | KPI Target | KPI Actual
T001 | Initial Project Planning & Requirements Gathering | 2024-03-01 | 2024-03-15 | In Progress | 15 deliverables completed by 3/15/24 | 9 / 15 (60%)
T002 | UI/UX Design Phase - Wireframing & Mockups | 2024-03-16 | 2024-03-31 | Pending | 8 design mockups delivered by 3/31/24 | 0 / 8 (0%)
T003 | Front-End Development - Core Modules | 2024-04-01 | 2024-05-15 | Pending | 18 features implemented by 5/15/24 | 0 / 18 (0%)
T004 | Back-End Development & API Integration | 2024-05-16 | 2024-06-30 | Pending | 12 APIs completed by 6/30/24 | 0 / 12 (0%)
T005 | Testing & Quality Assurance Cycle | 2024-07-01 | 2024-07-31 | Pending | 98% defect-free rate by 7/31/24 | 0 / 98% (N/A)
T006 | User Acceptance Testing (UAT) & Feedback | 2024-08-01 | 2024-08-15 | Pending | 95% approval rate from stakeholders | — (N/A)
T007 | Deployment & Go-Live Preparation | 2024-08-16 | 2024-09-30 | Pending | Zero downtime deployment by 9/30/24 | — (N/A)
Project Completion Rate | [5 empty] | 60% / 98%
This KPI monitoring table is designed for project timeline tracking with Freelancer-style interface. Status indicators reflect real-time progress and performance metrics.