## Worksheet
KPI Monitoring - Project Timeline
Large Business Template ¦ Quarterly Review ¦ Q3 2024
Project ID | Project Name | Timeline & Milestones |  |  |  | KPI Target | Current Status | Progress
|  | Start Date | Planned End Date | Actual End Date | Status Update
PJ001 | Enterprise CRM Integration | 2024-07-01 | 2024-10-31 | 2024-10-31 | Milestone Achieved - Data Migration Complete | 95% | On Track
PJ002 | Cloud Infrastructure Upgrade | 2024-06-15 | 2024-11-30 | — | In Progress - Phase 3 Deployment in Progress | 98% | On Track
PJ003 | Global Sales Portal Launch | 2024-05-10 | 2024-12-15 | — | Delayed - Regulatory Review Pending (Week 3) | 96% | At Risk
PJ004 | Customer Analytics Dashboard | 2024-08-15 | 2024-11-30 | — | In Progress - UI/UX Finalized & Testing Phase 2 | 99% | On Track
PJ005 | AI-Powered Support System | 2024-10-01 | 2025-03-31 | — | Planning Stage - Requirements Finalized, Dev Team Assigned | 97% | Delayed
Overall Project Health: | [5 empty] | 96.4% | On Track
Generated on¦ Last Updated: Q3 2024 Review Cycle