## Worksheet
KPI Monitoring - Project Timeline (Manager View)
Project Phase | Start Date | End Date | Planned Duration (Days) | Actual Duration (Days) | Status | KPI Target | KPI Achieved
Initiation & Planning | 2024-01-05 | 2024-01-15 | 10 | 9 | On Track | Finalize Scope & Budget (Jan 15) | Scope Approved (Jan 14)
Design & Development | 2024-01-16 | 2024-03-15 | 59 | 58 | On Track | Create MVP (Mar 10) | MVP Complete (Mar 9)
Testing & QA | 2024-03-16 | 2024-04-15 | 30 | - | Delayed (Est. 5 days) | Complete 95% Test Coverage (Apr 10) | 87% Coverage (Apr 4)
User Acceptance Testing | 2024-04-16 | 2024-05-15 | 30 | - | On Track | UAT Sign-off (May 10) | N/A (Pending)
Deployment & Go-Live | 2024-05-16 | 2024-05-31 | 15 | - | On Track | Cut-over Successful (May 30) | N/A (Pending)
Post-Launch Review | 2024-06-01 | 2024-06-15 | 15 | - | On Track | Closed Loop Report (Jun 14) | N/A (Pending)
Overall Project Status |  |  | 164 | 75 (Completed) | On Track | 90% on-time delivery rate | 87% achievement rate
Note:Status indicators are updated weekly. Delayed phases are flagged with estimated impact.
Last Updated:April 6, 2024 ¦ Prepared for Manager Review