## Worksheet
KPI Monitoring - Project Timeline (Multi-Page Template)
Project Phase | Activity | Start Date | End Date | KPI Target | Actual Progress (%) | Status
Planning Phase | Requirements Gathering | 2024-01-05 | 2024-01-25 | Complete 100% | 95% | In Progress
| Feasibility Study | 2024-01-26 | 2024-02-15 | Complete 100% | 78% | In Progress
| Project Charter Approval | 2024-02-16 | 2024-03-15 | Approved by Stakeholders | 35% | Delayed
Development Phase
Design & Development | UI/UX Design | 2024-03-16 | 2024-05-15 | Finalize all wireframes | 88% | In Progress
| Frontend Development | 2024-05-16 | 2024-07-31 | Complete 95% of components | 83% | In Progress
| Backend Development | 2024-05-16 | 2024-08-31 | APIs & Database Ready | 75% | In Progress
| Integration Testing | 2024-09-01 | 2024-10-31 | All modules integrated & tested | 5% | Delayed
Testing & Deployment Phase
Testing Phase | System Testing | 2024-11-01 | 2024-12-31 | All test cases passed | 0% | Delayed
| User Acceptance Testing (UAT) | 2025-01-01 | 2025-01-31 | 98% user satisfaction rate | 0% | Delayed
Post-Launch & Review Phase
Deployment & Evaluation | Production Deployment | 2025-02-01 | 2025-02-14 | All systems live & stable | 0% | Delayed
| Performance Monitoring (30 days) | 2025-02-15 | 2025-03-17 | 99.9% uptime achieved | 0% | Delayed
| Post-Mortem Review & Reporting | 2025-03-18 | 2025-04-18 | All lessons learned documented | 0% | Delayed
Overall Project Status:Delayed (Baseline schedule is behind by ~2 months)
Total KPIs Monitored:15 ¦KPIs Met:3 ¦In Progress:6 ¦Delayed:6