## Worksheet
KPI Monitoring - Project Timeline
Project ID | Project Name | Start Date | End Date | Status | KPI TargetKPI Actual | KPI Progress | Milestones
P001 | Website Redesign Launch | 2023-10-01 | 2024-01-31 | In Progress | 95% | 87% |  | UI/UX Design (Oct), Development (Nov-Dec), Testing (Jan)
P002 | Marketing Campaign Q4 | 2023-11-01 | 2023-12-31 | Completed | 50K Leads | 54K Leads |  | Campaign Setup (Nov), Execution (Nov-Dec), Review (Dec)
P003 | Customer Onboarding Portal | 2023-11-15 | 2024-03-15 | In Progress | 90% User Adoption | 68% |  | Prototype (Nov), Development (Dec-Feb), UAT (Mar)
P004 | IT Infrastructure Upgrade | 2023-12-01 | 2024-05-31 | In Progress | 99.9% Uptime | 98.7% |  | Assessment (Dec), Migration (Jan-Mar), Optimization (Apr-May)
P005 | Product Feature Launch | 2023-12-10 | 2024-04-30 | Delayed | 85% Adoption Rate | 45% |  | Requirements (Dec), Dev (Jan-Mar), Beta Testing (Apr)
Last Updated:¦ Template Version: Office Use v1.0