## Worksheet
Phase / Milestone | Start Date | Planned End Date | Actual End Date | KPI Target (e.g., % Complete) | Status
Project Initiation | 2024-01-05 | 2024-01-15 | 2024-01-14 | 100% | Completed
Requirements Analysis | 2024-01-16 | 2024-01-31 | 2024-01-30 | 95% | Completed
Design Phase | 2024-02-01 | 2024-02-15 | 2024-02-16 | 85% | Delayed
Development (Frontend) | 2024-02-16 | 2024-03-15 | -- | 70% | On Track
Development (Backend) | 2024-02-16 | 2024-03-15 | -- | 68% | On Track
Testing Phase | 2024-03-16 | 2024-04-15 | -- | 35% | On Track
User Training & Documentation | 2024-04-16 | 2024-04-30 | -- | 15% | On Track
Go-Live & Deployment | 2024-05-01 | 2024-05-15 | -- | 5% | On Track
Total Project Progress | 76% |  |  |  | On Track