## Worksheet
KPI Monitoring - Project Timeline
Template Type: Project Timeline ¦ Style/Version: Small Business
Reporting Period: January 2024 - December 2024
Task ID | Task Name | Start Date | End Date | Budget (USD) | Status | KPI Target
T001 | Project Initiation & Planning | 2024-01-05 | 2024-01-25 | $8,500 | Completed | Define scope & deliverables by Jan 25
T002 | Market Research & Analysis | 2024-01-30 | 2024-03-15 | $15,750 | In Progress | Survey 50+ clients by Feb 28
T003 | Design Phase (UI/UX) | 2024-03-18 | 2024-05-10 | $24,300 | In Progress | Final prototypes approved by May 5
T004 | Development & Testing | 2024-05-13 | 2024-08-15 | $68,900 | In Progress | Alpha release by June 30
T005 | User Acceptance Testing (UAT) | 2024-08-18 | 2024-09-30 | $12,500 | Delayed | Feedback from 3 key departments collected by Sep 15
T006 | Final Deployment & Training | 2024-10-01 | 2024-10-31 | $9,850 | Completed | All users trained by Oct 31
T007 | Post-Launch Review & Optimization | 2024-11-01 | 2024-12-31 | $5,450 | In Progress | KPIs reviewed weekly; improvements implemented by Dec 31
Generated on: