## Worksheet
KPI Monitoring - Project Timeline (Startup)
Project Phase | Start Date | End Date | Status | KPI Target | Progress (Current)
Market Research & Validation | 2024-01-15 | 2024-03-15 | In Progress | 3,500 Validated Users | 72%
Product Design & Prototyping | 2024-03-16 | 2024-05-31 | Pending | 5 Designs Reviewed, 3 Finalized | 0%
Development Sprint 1 | 2024-06-01 | 2024-07-31 | Pending | Core Features: MVP Ready (v1.0) | 0%
Development Sprint 2 | 2024-08-01 | 2024-11-30 | Pending | MVP + UX Enhancements Released (v1.5) | 0%
Alpha Testing & Feedback | 2024-12-01 | 2025-01-31 | Pending | ≥ 95% User Satisfaction Rate (Score ≥ 4.5) | 0%
Beta Launch & Scaling | 2025-02-01 | 2025-11-30 | Pending | Reach 5,000 Active Users; $35K MRR | 0%