## Worksheet
Project Phase | Start Date | End Date | Target KPI | Actual Result | Status | Progress (%)(Visual)
Initiation & Planning | 2024-01-05 | 2024-01-19 | Project Charter Approved | Yes (Jan 17) | On Track | 85%
Design & Development | 2024-01-20 | 2024-03-15 | Core Features Complete | In Progress (Mar 5) | On Track | 68%
Testing & QA | 2024-03-16 | 2024-04-15 | All Critical Bugs Resolved | Pending (Expected Apr 12) | On Track | 75%
Deployment | 2024-04-16 | 2024-05-15 | System Live & Stable | N/A (Not Started) | Delayed (Planned Start)
Post-Launch Review | 2024-05-16 | 2024-05-31 | All Feedback Addressed | N/A (Future) | Delayed (Phase Not Started)