## Worksheet
KPI Monitoring - Project Tracker (Business Use)
Project ID | Project Name | Department | Start Date | Target End Date | Status | KPI 1: Completion % | KPI 2: Budget Usage (%) | KPI 3: Milestone Achieved
PJ001 | Website Redesign Initiative | Marketing & Web Development | 2024-01-15 | 2024-06-30 | Ongoing | 78% | 65% | M1: Design Finalized, M2: Development Phase 1 Complete
PJ002 | CRM System Upgrade | IT & Sales Operations | 2024-03-10 | 2024-11-15 | Ongoing | 56% | 49% | M1: Requirements Analysis Complete, M2: API Integration Started
PJ003 | Product Launch 2024 Q3 | R&D & Marketing | 2024-01-05 | 2024-10-31 | Ongoing | 89% | 76% | M1: Prototype Tested, M2: Beta Launch Complete, M3: Customer Feedback Analyzed
PJ004 | Employee Training Program | Hr Development | 2024-05-15 | 2024-12-31 | Ongoing | 34% | 38% | M1: Curriculum Finalized, M2: Module 1 Training Conducted
PJ005 | Office Relocation Project | FACILITIES & Admin | 2024-07-01 | 2024-11-30 | Delayed - Pending Approval | 51% | 69% | M1: Site Survey Complete, M2: Contractor Selection Delayed by Vendor Audit
PJ006 | Customer Support Automation | IT & Customer Service | 2024-04-15 | 2025-03-31 | Ongoing | 68% | 74% | M1: Chatbot Model Trained, M2: Integration Testing in Progress
Last Updated:2024-06-15