## Worksheet
Daily Project Tracker - KPI Monitoring
Project ID | Project Name | Team Member(s) | Status (Today) | KPI Target (Daily) | KPI Actual (Today) | Variance (+/-) | Notes / Actions
PJ001 | Website Redesign | Alice Johnson, Bob Smith | In Progress | 35% | 38% | +3% | Frontend components completed ahead of schedule. Next Steps:Finalize responsive design testing.',
PJ002 | Marketing Campaign Q3 | Carol Davis, David Lee | On Track | 15% | 14% | -1% Next Steps:Review social media analytics report.',
PJ003 | Customer Portal Upgrade | Emma Wilson, Frank Brown | Delayed (Pending Review) | 40% | 32% | -8% Next Steps:Schedule meeting with stakeholders to address feedback.',
PJ004 | Product Launch Preparation | Grace Taylor, Henry Moore | On Track | 25% | 26% | +1% Next Steps:Finalize launch event logistics.',
PJ005 | Data Migration Phase 1 | Ivy Clark, Jack White | Completed (Pending QA) | 100% | 100% | +0% Next Steps:Begin QA testing on migrated data.',