## Worksheet
KPI Monitoring - Project Tracker (Data Version)
Project ID | Project Name | Owner | Start Date | Target Completion Date | Status | KPI 1: Milestone Progress (%) | KPI 2: Budget Utilization (%) | KPI 3: Risk Level (1-5) | Last Updated
PJ001 | Website Redesign | Alice Johnson | 2024-01-15 | 2024-05-31 | On Track | 78% | 65% | 2 | 2024-03-10
PJ002 | Data Migration Initiative | Robert Smith | 2024-01-10 | 2024-06-15 | Delayed | 55% | 89% | 4 | 2024-03-10
PJ003 | Cybersecurity Upgrade | Sarah Williams | 2024-02-28 | 2024-11-30 | On Track | 95% | 76% | 1 | 2024-03-10
PJ004 | Marketing Automation Setup | Michael Brown | 2024-03-15 | 2024-12-31 | On Track | 67% | 58% | 3 | 2024-03-10
PJ005 | Customer Feedback Portal | Jennifer Lee | 2024-01-25 | 2024-10-31 | Completed | 100% | 93% | NA | 2024-03-10