## Worksheet
Project ID | Project Name | Owner | Status | Start Date | End Date | Budget (USD) | KPI Target | KPI Actual
PJ001 | Website Redesign Initiative | Emily Chen | In Progress | 2023-10-15 | 2024-03-31 | $85,000 | 95% User Satisfaction | 92%
Milestone: UX Prototype Completed (Nov 30, 2023)
PJ002 | Mobile App Launch | James Wilson | Planning | 2023-11-01 | 2024-06-30 | $150,000 | 85% App Store Rating | N/A
Milestone: Beta Testing Phase (Jan 15, 2024)
PJ003 | CRM Integration | Sophia Martinez | On Hold | 2023-12-01 | 2024-11-30 | $65,000 | 98% Data Sync Accuracy | 97%
Warning: Project PJ003 delayed by 3 weeks due to vendor issues.
PJ004 | Marketing Campaign Q1 | Liam Brown | Completed | 2023-10-01 | 2023-12-31 | $45,000 | $5M Revenue Increase | $5.6M
Total Projects: | [5 empty] | $345,000 | Average KPI Achievement: | 92.5%