## Worksheet
Project Tracker - KPI Monitoring
Project ID | Project Name | Department | Scheduled Start Date | Scheduled End Date | Actual Start Date | Actual End Date | Status | KPI Target (%) | KPI Achieved (%)
PJ001 | Website Redesign Initiative | Marketing | 2024-03-15 | 2024-06-30 | 2024-03-18 | 2024-06-15 | Completed | 95% | 97%
PJ002 | CRM System Upgrade | IT Department | 2024-04-01 | 2024-11-30 | 2024-04-05 | - | In Progress | 90% | 76%
PJ003 | Customer Loyalty Program | Customer Success | 2024-02-10 | 2024-10-31 | 2024-03-15 | - | In Progress | 85% | 68%
PJ004 | Supply Chain Optimization | Operations | 2024-01-20 | 2024-12-31 | 2024-01-30 | - | Delayed | 88% | 59%
PJ005 | Product Launch Q3 | Product Development | 2024-06-15 | 2024-12-31 | - | - | Planning Phase | 92% | 0%
Generated on¦ Project Tracker - KPI Monitoring Template ¦ Professional Style