## Worksheet
Quarterly Project Tracker - KPI Monitoring
Q2 2024 ¦ Project Performance & Key Metrics Overview
Project ID | Project Name | Owner | Key Performance Indicators (KPIs)
|  |  | Target | Actual | Status | Comments
PJ001 | Website Redesign Launch | Alice Johnson | 100% Completion by Jun 30 | 98% | On Track | Few minor UI adjustments pending.
PJ002 | Mobile App Development | Robert Smith | 10,000 Downloads by Jun 30 | 9,256 | On Track | Marketing campaign boosted early adoption.
PJ003 | CRM Integration Upgrade | Sarah Williams | 95% System Uptime by Jun 30 | 94.2% | Delayed | Server migration caused brief downtime.
PJ004 | Customer Onboarding Process Revamp | Michael Brown | 50% Reduction in Onboarding Time by Jun 30 | 56% | Completed | Met target ahead of schedule.
PJ005 | Cloud Migration Phase 1 | Emily Davis | 100% Data Transfer Completed by Jun 30 | 99.7% | On Track | All critical data moved; final sync pending.
PJ006 | Marketing Campaign Q2 | James Wilson | Generate 5,000 Leads by Jun 30 | 4,875 | On Track | Close to target; final week to boost.
PJ007 | Employee Training Program Rollout | Lisa Garcia | 85% Participation Rate by Jun 30 | 83% | Delayed | Scheduled sessions impacted by team vacations.
PJ008 | Data Analytics Dashboard Launch | David Lee | 15+ Dashboards Live by Jun 30 | 14 | On Track | Last dashboard in final testing phase.
PJ009 | Security Audit & Compliance Update | Grace Kim | 100% Compliance Achieved by Jun 30 | 97% | Delayed | Third-party dependency delay in audit.
PJ010 | Internal Communication Platform Upgrade | Thomas Hall | All Users Trained by Jun 30 | 92% | On Track | Pending training for remote teams.
Total Projects: |  |  | 10 | 9 | 2 Completed ¦ 6 On Track ¦ 2 Delayed
Last Updated: May 30, 2024 ¦ Prepared by KPI Monitoring Team