## Worksheet
KPI Monitoring - Schedule Planner (Manager View)
Project: Strategic Growth Initiative ¦ Period: Q3 2024 ¦ Last Updated: June 5, 2024
Task ID | Task Name | Timeline (Start - End) |  |  | Responsible Team | KPI Target(Metric) | Current Status(Progress %) | Actual Result(Achieved?)
|  | Planned Start | Planned End | Actual End (if applicable)
T001 | Project Kickoff | 2024-07-01 | 2024-07-03 | - | Executive Team | N/A(Initiation) | 100% | Yes(Completed)
T002 | Market Research Phase | 2024-07-04 | 2024-07-15 | - | Marketing & Analytics | KPI: 5,000 survey responses (Response Rate) | 68% | Partially Achieved (3,421 received)
T003 | Product Development (Phase 1) | 2024-07-16 | 2024-08-31 | - | R&D Team | KPI: MVP completed by target (Deliverable) | 57% | Delayed (Target: Aug 31)
T004 | User Testing & Feedback | 2024-09-01 | 2024-10-15 | - | QA & UX Team | KPI: 85% user satisfaction (Score) | 0% | Not Started
T005 | Final Launch & Go-to-Market | 2024-10-16 | 2024-11-30 | - | Marketing & Sales Team | KPI: 5,000 new customers (Acquisition) | 0% | Not Started
Overall Progress: | [5 empty] | 64% | 64% | On Track (with delays in Phase 1 & Testing)(Note: Launch delayed by 1 week)
*All timelines are subject to change based on stakeholder feedback and resource availability. Please review weekly.