## Worksheet
Task ID | Task Name | Assigned To | Department | Start Date | Due Date | Priority | Status | Progress (%) | KPI Target | Actual Result | Completion Date
T001 | Develop Q3 Marketing Strategy | Sarah Johnson | Marketing | 2024-07-01 | 2024-07-31 | High | In Progress | 65% | 12 campaigns launched | 9 campaigns launched
T002 | Launch New Product Line | James Wilson | Product Development | 2024-06-15 | 2024-09-30 | Medium | On Track | 40% | 10 new products | 4 new products
T003 | Customer Support Training | Lisa Chen | HR & Operations | 2024-07-10 | 2024-07-25 | Low | In Progress | 75% | 100% team trained | 70% team trained | 2024-07-25
T004 | Website Redesign Project | Alex Rivera | IT & Web Development | 2024-06-01 | 2024-08-31 | High | Delayed | 30% | Fully responsive & optimized | 30% completed (design phase)
T005 | Annual Performance Review | Michael Brown | HR & Operations | 2024-07-15 | 2024-09-15 | Low | On Track | 20% | 100% employees reviewed | 5% completed
T006 | Inventory Management System Upgrade | Emma Davis | Logistics & Supply Chain | 2024-05-20 | 2024-10-31 | Medium | In Progress | 55% | Zero stock discrepancies | 3% discrepancy rate
T007 | Client Onboarding Process Optimization | Daniel Kim | Customer Success | 2024-07-05 | 2024-11-30 | Low | On Track | 15% | Reduce onboarding time by 30% | 4 days average vs. target of 3 days
T008 | Social Media Campaign - Q3 | Olivia Martinez | Marketing | 2024-07-15 | 2024-09-30 | High | In Progress | 45% | 1.2M impressions, 15% engagement rate | 750K impressions, 10.3% engagement
T009 | Monthly Financial Reporting Automation | Robert Taylor | Finance & Accounting | 2024-06-10 | 2024-09-15 | Medium | On Track | 70% | 95% report accuracy, 2-day turnaround | 94.3% accuracy, 2.1-day average
T010 | Cybersecurity Compliance Audit | Sophia Lee | IT & Security | 2024-07-15 | 2024-10-31 | High | In Progress | 25% | 100% compliance with ISO 27001 | 63% compliance identified