## Worksheet
KPI Monitoring - Planning View Time Tracker
Tracking Key Performance Indicators Over Planned Timeline
Activity / Task | KPI Name | Target Value | Planned Start Date | Planned End Date | Status (Planned) | Budget (Hours) | Responsible Team Member
Project Kickoff Meeting | Initiation Rate | 100% | 2024-04-01 | 2024-04-03 | In Planning | 8 | Jane Smith
Requirement Gathering Phase | Requirement Accuracy Rate | 95% | 2024-04-04 | 2024-04-15 | In Planning | 36 | John Doe
Design & Prototyping Phase | Design Quality Index (DQI) | 90+ | 2024-04-16 | 2024-05-15 | In Planning | 80 | Alice Johnson
Development Sprint 1 - Core Features | Sprint Completion Rate (SCR) | 95%2024-05-16 | 2024-06-13 | In Planning | 88 | Robert Brown
Testing & QA Phase (Alpha) | Bug Density (Bugs per 1K LOC) | <52024-06-14 | 2024-07-18 | In Planning | 64 | Sarah Wilson
User Acceptance Testing (UAT) | User Satisfaction Score (USS) | >85%2024-07-19 | 2024-08-16 | In Planning | 48 | Marcus Lee
Deployment & Go-Live Preparation | Deployment Success Rate (DSR) | >98%2024-08-17 | 2024-08-31 | In Planning | 56 | Linda Chen