## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Budgeted Hours | Actual Hours Spent | KPI Target (Hours) | KPI Actual (Hours) | KPI Achievement (%)
TASK001 | Project Planning & Setup | John Doe | 2024-04-01 | 2024-04-15 | In Progress | 30 | 27.5 | 30 | 27.5 | 91.7%
TASK002 | Data Collection & Analysis | Jane Smith | 2024-04-16 | 2024-05-15 | Completed | 60 | 58.3 | 60 | 58.3 | 97.2% th>
TASK003 | Design Phase Implementation | Mike Johnson | 2024-05-16 | 2024-06-15 | In Progress | 45 | 38.7 | 45 | 38.7 | 86.0%
TASK004 | Final Review & Reporting | Sarah Brown | 2024-06-16 | 2024-07-15 | Pending | 35 | 0 | 35 | 0 | 0.0%
Total KPIs: | [8 empty] | 175 | 124.5 | 88.3%
Notes:KPI Achievement (%) is calculated as (KPI Actual / KPI Target) * 100. Status values include Pending, In Progress, Completed.