## Worksheet
Logistics Planning - Client View
Phase | Activity | Description | Responsible Party | Status | Due Date
Planning & Strategy
1.1 | Initial Requirements Gathering | Collect client logistics needs, delivery expectations, and key performance indicators. | Account Manager | In Progress | 2024-05-15
1.2 | Supply Chain Assessment | Analyze current logistics network, identify bottlenecks and risks. | Logistics Analyst | Pending | 2024-05-20
Route & Network Design
2.1 | Optimized Route Mapping | Develop efficient delivery routes using real-time traffic and geographical data. | Network Planner | Pending | 2024-05-25
2.2 | Warehouse Location Analysis | Evaluate strategic warehouse placements to reduce transit times and costs. | Supply Chain Consultant | Pending | 2024-05-30
Technology & Integration
3.1 | Tracking System Setup | Integrate GPS and real-time tracking into client dashboard. | IT Integration Specialist | Pending | 2024-06-05
3.2 | Data Sync with ERP System | Ensure seamless data flow between logistics platform and client’s ERP. | Systems Engineer | Pending | 2024-06-10
Implementation & Testing
4.1 | Pilot Run Execution | Conduct a 2-week pilot with selected delivery routes. | Operations Manager | Pending | 2024-06-15
4.2 | User Training Sessions (Client Team) | Train client staff on using tracking tools and reporting dashboards. | Training Coordinator | Pending | 2024-06-18
Review & Sign-off
5.1 | Performance Report Delivery | Provide KPI dashboard and performance summary post-pilot. | Data Analyst | Pending | 2024-06-22
5.2 | Client Final Approval | Client review and formal sign-off on logistics plan. | CFO / Client Representative | Pending | 2024-06-30