## Worksheet
Logistics Planning Business Plan Template (Extended Version)
Item | Description | Planning Parameters
|  | Target Date | Responsible Party | Status | Progress (%) | Notes / Remarks
1. Supply Chain & Logistics Infrastructure
Supplier Onboarding | Establish relationships with primary and backup suppliers for key materials. | 2024-06-30 | Purchasing Team | In Progress | 85% | Onboarding 4 out of 5 critical suppliers.
Warehouse Facilities | Identify and secure warehouse locations across target regions. | 2024-07-15 | Operations Manager | Not Started | 0% | Site selection pending vendor approval.
Fleet Acquisition | Purchase and equip transport vehicles for domestic distribution. | 2024-08-10 | Logistics Director | In Progress | 65% | 3 of 5 trucks delivered; rest scheduled for next week.
IT Systems Integration | Implement WMS and TMS for real-time tracking and inventory control. | 2024-09-01 | IT Department | In Progress | 55% | System testing phase underway; pilot with 3 sites.
2. Transportation & Distribution Strategy
Route Optimization | Develop efficient delivery routes using GPS and analytics tools. | 2024-07-31 | Distribution Planner | In Progress | 70% | Optimization engine integrated; pending validation.
Carrier Contracts | Negotiate and sign agreements with third-party logistics providers. | 2024-08-15 | Procurement Lead | Pending Approval | 40% | Final review by legal team; expected completion on Aug 1.
Delivery KPIs | Define and monitor performance metrics for on-time delivery, fuel efficiency, etc. | 2024-06-30 | KPI Coordinator | Completed | 100% | Dashboard live and updated weekly.
3. Inventory & Warehouse Management
Inventory Forecasting Model | Develop statistical model to predict demand and stock requirements. | 2024-07-25 | Data Analyst | In Progress | 80% | Model trained on 3 years of historical data.
Replenishment Strategy | Set reorder points, safety stock levels, and trigger mechanisms. | 2024-08-05 | Inventories Lead | Not Started | 0% | Pending finalization of demand forecasts.
ABC Analysis Implementation | Categorize SKUs by value and turnover rate for prioritized management. | 2024-08-15 | Inventory Analyst | In Progress | 60% A-class items mapped; B/C follow-up pending.
4. Risk Management & Contingency Planning
Disruption Response Plan | Create protocols for supplier failure, natural disasters, and transport delays. | 2024-09-30 | Risk Manager | In Progress | 50% Scenario modeling in progress; drills scheduled for Q4.
Emergency Stock Locations | Identify and pre-position critical inventory in high-risk zones. | 2024-08-31 | Operations Lead | In Progress | 75% Two emergency sites secured; one under negotiation.
Insurance Coverage Review | Verify adequacy of cargo, liability, and business interruption insurance. | 2024-07-15 | Finance & Compliance | Completed | 100% All policies renewed with expanded coverage.
5. Performance Monitoring & Continuous Improvement
Monthly Logistics Review Meeting | Hold executive meetings to assess KPIs, issues, and improvement initiatives. | First Monday of every month | CPO & Operations Lead | Scheduled | 100% First meeting held on 2024-06-03.
Feedback Loop Integration | Collect and analyze feedback from field teams and customers. | Ongoing | Customer Service Lead | In Progress | 90% Monthly survey deployed; results used in optimization.
Annual Plan Review | Evaluate performance against initial goals and revise strategy for next cycle. | December 31, 2024 | CEO & Board | Pending Initiation | 0% Preparation starts in Q4; no formal schedule yet.
Template Version: Extended Logistics Planning - Business Plan (v2.1)
Generated on: