## Worksheet
Logistics Planning - Business Plan Template
Office Use ¦ Version 1.0 ¦ Prepared for Internal Business Strategy Planning
Project Phase | Key Activities | Responsible Department | Timeline (Start - End) | Status | Budget Allocation ($)
Planning & Requirements Gathering | Identify delivery zones, demand forecasting, resource assessment | Supply Chain Management | Jan 01 - Jan 15 | In Progress | 25,000
Route Optimization & Network Design | Analyze transportation routes, warehouse placement, load consolidation | Logistics Engineering | Jan 16 - Feb 10 | Not Started | 45,000
Fleet & Equipment Procurement | Select and order vehicles, maintenance tools, tracking devices | Purchasing Department | Feb 11 - Mar 31 | Not Started | 320,000
Warehouse Setup & Automation Integration | Build storage facilities, install inventory management software | Facilities & IT Departments | Mar 15 - May 15 | Not Started | 280,000
Driver Recruitment & Training | Hire delivery personnel, conduct safety and protocol training | Human Resources & Operations | Apr 1 - Apr 30 | Not Started | 65,000
Pilot Run & System Testing | Launch trial logistics operations, monitor performance metrics | Operations Team | May 16 - Jun 30 | Not Started | 75,000
Total Estimated Costs: |  |  |  |  | $810,000