## Worksheet
Logistics Planning - Business PlanPlanning View - Version 1.0
Logistics Planning Overview
Plan Phase | Key Objective | Target Timeline (Weeks) | Status | Budget Allocation ($) | Responsible Team
Needs Assessment | Evaluate current logistics capabilities and gaps. | 1-4 | Pending | 25,000 | Operations Team
Network Design | Design optimal distribution network layout. | 5-8 | In Progress | 40,000 | Supply Chain Architects
Fleet Strategy | Determine vehicle types, capacity, and procurement plan. | 9-12 | Pending | 75,000 | Fleet Management
Warehouse Optimization | Identify and configure strategic warehouse locations. | 13-16 | Pending | 50,000 | Distribution Team
Technology Integration | Implement TMS and WMS systems for real-time tracking. | 17-20 | Pending | 90,000 | Tech & Analytics Group
Supplier Onboarding | Onboard and qualify key logistics partners. | 21-24 | Pending | 15,000 | Procurement Team
Pilot Launch | Execute pilot program in 2 regional zones. | 25-28 | Pending | 60,000 | Field Operations
Full Rollout | Scale logistics network nationwide. | 29-36 | Pending | 180,000 | All Teams