## Worksheet
Logistics Planning Business Plan
Report Version ¦ Prepared for Strategic Decision-Making
Project Phase | Key Activity | Responsible Team | Target Date | Status | Budget Allocated ($)
Phase 1: Planning & Assessment | Conduct Supply Chain Gap Analysis | Logistics Strategy Team | 2024-03-15 | In Progress | 45,000.00
Phase 2: Route Optimization | Map and Optimize Delivery Routes Using GIS Tools | Operations & Tech Integration Team | 2024-04-10 | Pending | 68,500.00
Phase 3: Warehouse Expansion | Design and Secure New Regional Distribution Center | Facility Planning & Procurement Team | 2024-05-20 | Pending | 1,250,000.00
Phase 4: Vendor Sourcing | Select and Contract Third-Party Logistics Providers (3PLs) | Procurement & Contracts Team | 2024-05-15 | Pending | 95,300.00
Phase 5: Technology Implementation | Deploy Real-Time Tracking & Inventory Management System | IT & Logistics Systems Team | 2024-06-30 | Pending | 187,450.00
Phase 6: Training & Rollout | Train Staff and Implement New Logistics Protocols | HR & Operations Team | 2024-07-15 | Pending | 78,900.00
Phase 7: Monitoring & Review | Establish KPIs and Conduct Monthly Performance Reviews | Performance Analytics Team | Ongoing | Pending | 50,000.00
Total Budget Allocated: |  |  |  |  | $1,975,150.00
This report was generated on 2024-02-28. All data is subject to change based on ongoing planning and market conditions.