## Worksheet
Logistics Planning - Startup Business Plan
Section | Description | Key Metrics | Timeline (Months) | Status
Sourcing & Procurement | Identify suppliers, negotiate terms, and establish procurement protocols. | Number of suppliers, average lead time, cost per unit | 1-3 | In Progress
Warehouse & Storage Setup | Select and set up primary and backup storage locations. | Square footage, capacity, cost per sq. ft., automation level | 2-6 | To Do
Transportation & Carrier Management | Choose carriers, negotiate contracts, and integrate tracking systems. | Number of active carriers, on-time delivery rate, freight cost per mile | 3-8 | To Do
Inbound Logistics | Plan for receiving and processing incoming goods. | Receiving time, error rate, inventory accuracy percentage | 1-5 | In Progress
Outbound Logistics | Design order fulfillment and delivery workflows. | Average order cycle time, shipping cost per order, customer satisfaction score | 4-10 | In Progress
Inventory Management System | Implement real-time tracking software (e.g., WMS/ERP). | System uptime, data accuracy rate, update frequency | 5-9 | To Do
Demand Forecasting Model | Develop predictive models based on market trends and historical data. | MSE (Mean Squared Error), forecast accuracy percentage, seasonal adjustment factor | 6-12 | To Do
Emergency & Contingency Planning | Prepare response plans for disruptions (e.g., natural disasters, supply chain delays). | Disruption response time, recovery rate, alternate supplier readiness | Ongoing | In Progress