## Worksheet
Logistics Planning - Tracking View
Task ID | Activity Description | Assigned To | Start Date | Due Date | Status | Progress (%)
#LP-001 | Sourcing Raw Materials from Supplier A | Procurement Team | 2023-10-05 | 2023-10-15 | Completed | 100%
#LP-002 | Warehouse Capacity Assessment | Logistics Manager | 2023-10-10 | 2023-10-18 | Pending | 65%
#LP-003 | Transportation Route Optimization | Fleet Coordinator | 2023-10-12 | 2023-10-25 | Pending | 45%
#LP-004 | Inventory Level Check & Replenishment Planning | Supply Chain Analyst | 2023-10-15 | 2023-10-28 | Pending | 35%
#LP-005 | Delivery Schedule Coordination with Clients | Customer Service Lead | 2023-10-18 | 2023-11-05 | Delayed | 70%
#LP-006 | Third-party Logistics (3PL) Contract Review | Legal & Contracts Team | 2023-10-20 | 2023-11-15 | Pending | 55%
Total Tasks:6 ¦Completed:1 ¦In Progress:4 ¦Delayed:1