## Worksheet
Week Ending | Region | Delivery Target (Units) | Actual Deliveries (Units) | On-Time Rate (%) | Status | Remarks/Issues
Week of May 1 - May 7, 2024
May 7, 2024 | North America | 15,000 | 14,850 | 99.0% | On Track | Minor delay due to weather; resolved by May 6.
May 7, 2024 | Europe | 10,500 | 10,375 | 98.8% | On Track | Slight delay in customs clearance; no impact on delivery timeline.
May 7, 2024 | APAC | 18,000 | 17,950 | 99.7% | On Track | High demand observed; additional capacity deployed.
Week of May 8 - May 14, 2024
May 14, 2024 | North America | 16,000 | 15,980 | 99.9% | On Track | No issues reported.
May 14, 2024 | Europe | 11,000 | 10,855 | 98.7% | Delayed | Port congestion caused 48-hour delay; rescheduled delivery.
May 14, 2024 | APAC | 17,500 | 17,300 | 98.9% | On Track | High volume handled efficiently; team performance excellent.
Total Weekly Performance |  | 57,500 | 54,763 | 95.2% | Overall progress: 88% of weekly target achieved; action plan in place for next week.
Note:This template is designed for weekly logistics planning and can be exported to Excel using standard tools. Adjust data as needed each week.