## Worksheet
Task | Assigned To | Priority | Schedule |  |  |  | Status
|  |  | Start Date | End Date | Due Time | Duration (hrs)
Pickup Delivery Schedule Coordination | Logistics Team Lead | High | 2024-04-05 | 2024-04-07 | 16:30 | 8 | Pending
Route Optimization Analysis | Operations Analyst | High | 2024-04-06 | 2024-04-10 | 15:00 | 16 | In Progress
Carrier Contract Review | Procurement Manager | Medium | 2024-04-08 | 2024-04-11 | 13:30 | 6 | In Review
Fleet Maintenance Check (Daily) | Mechanic Team | High | 2024-04-05 | Ongoing | 08:30 | 4 | Completed
Inventory Audit (Weekly) | Warehouse Supervisor | Medium | 2024-04-05 | 2024-04-13 | 17:00 | 18 | Pending
Delivery Performance Report Compilation | Data Analyst | Low | 2024-04-12 | 2024-04-15 | 18:00 | 6 | Not Started
Total Tasks: |  |  | 6