## Worksheet
Task | Responsible Party | Schedule |  |  | Status | Notes/Updates
|  | Start Date | Due Date | Frequency
Pickup Schedule Coordination | Logistics Manager | 2023-10-01 | 2023-10-05 | Daily | In Progress | Confirm with all suppliers.
Vehicle Maintenance Check | Fleet Technician | 2023-10-01 | 2023-10-03 | Weekly | Completed | All 5 trucks inspected.
Route Optimization Review | Operations Analyst | 2023-10-04 | 2023-10-06 | Biweekly | Pending Approval | Awaiting input from logistics lead.
Inventory Audit (Warehouse A) | Warehouse Supervisor | 2023-10-05 | 2023-10-07 | Monthly | In Progress | Ongoing; 85% complete.
Delivery Confirmation Logging | Field Coordinator | 2023-10-01 | 2023-10-31 | Daily | In Progress | Updated via mobile app.
Driver Training Session | HR & Safety Officer | 2023-10-10 | 2023-10-10 | Quarterly | Scheduled | All drivers confirmed attendance.
Supply Chain Risk Assessment | Risk Management Team | 2023-10-15 | 2023-10-17 | Monthly | Pending | Needs data from procurement.
Equipment Calibration (GPS Devices) | Tech Support Specialist | 2023-10-18 | 2023-10-19 | Bimonthly | Not Started | All 15 units scheduled.
Weekly Logistics Report Submission | Logistics Coordinator | 2023-10-01 | 2023-10-31 | Weekly | In Progress | Final version due Friday.
End of Schedule — Review Period: October 1–31, 2023