## Worksheet
Logistics Planning - Financial View Chore Chart
Task | Responsible Party | Start Date | End Date | Status | Budget (USD) | Actual Cost (USD) | Variance (USD) | % Complete | Priority | Notes
Purchase Inventory | Procurement Team | 2024-05-01 | 2024-05-15 | In Progress | $15,000.00 | $13,876.43 | $+1,123.57 (Favorable) | 92% | High | Delivery scheduled for May 14
Transportation Arrangements | Fleet Coordinator | 2024-05-03 | 2024-05-18 | Scheduled | $8,500.00 | $- | $- | 15% | Medium
Warehouse Receiving & Inspection | Logistics Supervisor | 2024-05-16 | 2024-05-17 | Pending | $3,200.00 | $- | $- | 5% | High
Distribution Planning & Routing | Demand Planner | 2024-05-18 | 2024-05-21 | Pending | $6,800.00 | $- | $- | 3% | High
Delivery to Retail Outlets | Distribution Team | 2024-05-22 | 2024-05-31 | Pending | $18,750.00 | $- | $- | 0% | High
Total Budget & Summary | [8 empty] | $52,250.00 | $13,876.43
Overall Financial Status: | [8 empty] | $+38,373.57 (Favorable) | Expected